## Sheet2
PROJECT NAME: Furniture Store App
Test Script Name: |  | Purchase Chair Test Script
Scenario/Purpose: |  | Test application for Functionality
Prerequisites: |  | Must have an app account
Name of Tester: |  | John Smith
Step: | Description: |  | Expected Results: | Pass: | Fail: | Defects/Comments:
1 | Log into user account |  | The app will sign into the user's account | X |  | None
2 | Click on the name and or picture of the chair |  | User will be taken to the product's page | X |  | None
3 | In the book quantity dropdown menu, select "0" chairs |  | The app will prevent the user from confirming a zero quantity. |  | X | The app does not prevent the user. The zero quantity is accepted, and when the "Purchase" button is clicked, the user is taken to a page that says "An error has occurred."
4 | Select "1" chair |  | The app will register 1 chair to purchase | X |  | None
5 | Click the "Purchase" button |  | User will be taken to the shopping cart page | X |  | None
6 | Review Items and click "Proceed to Checkout" |  | User will be taken to the checkout page | X |  | None
7 | Leave address information blank |  | The app will prompt the user to enter address information | X |  | None
8 | Enter correct address information |  | The address information will be saved | X |  | None
9 | Leave payment information blank |  | The app will prompt the user to enter payment information | X |  | None
10 | Enter correct payment information |  | The payment information will be saved | X |  | None
11 | Click "Confirm Purchase" button |  | The app will process the purchase and return the user to the main menu | X |  | None
12 | Click "My Account" in the top right corner |  | User will be taken to their account page | X |  | None
13 | Click "My Receipts" |  | The app will display the user's past purchases | X |  | The receipts are shown to the user, but the formatting is bad. The receipts read "Item=FoldingChair,Price=15.50,Quantity=1" etc. More formatting is needed.
14 | Confirm that quantity, address, purchase information and price are correct |  | The app will successfully record and display information about the user's purchases | X |  | None
15 | Sign out of account |  | User's account will be signed out | X |  | None